## Sheet1 (hidden)
| When does buyer need raw kelp |  | 2025-05-20 | Edit
| How many lbs to they want |  | 50000 | Edit
| How many lbs can you harvest/process per day |  | 5000 | Edit
| How many days will it take to harvest |  | 10 | Calculated
| Growing days |  | 170 | Edit
| Harvest Window | Early | 2025-05-10
|  | Late | 2025-05-20
Touchpoints with buyers after the season | Orders for next season |  | 2025-07-30 | Constant
| Season Debrief |  | 2025-08-01
| Confirm Payment Received | See payment terms | 2025-07-25
| Send Invoice | ASAP | 2025-06-25
| Confirm Buyer accepts order | See inspection period | 2025-06-24
| Confirm receipt of order |  | 2025-06-19
Processing and shipping | Estimated arrival at buyer | Ask shipper | 2025-06-19
| Shipping deadline | See contract terms | 2025-06-05
| Processing window | Finish | 2025-05-22
|  | Start | 2025-05-10
Touchpoints with buyers during the season | May growth update / harvest plan update | 1 week before harvest | 2025-05-03
| April growth update 2 |  | 2025-04-26
| April growth update 1 |  | 2025-04-12
| March growth update 2 |  | 2025-03-29
| March growth update 1 |  | 2025-03-15
| February growth update |  | 2025-02-06
| January growth update |  | 2025-01-07
| Post outplanting update |  | 2024-12-08
Farm Operation Deadlines | Outplanting Window | Early | 2024-11-21
|  | Late | 2024-12-01
| Gear Deployment |  | 2024-11-14
| Line Preparation |  | 2024-11-07
| Receive New Gear |  | 2024-10-31
| Order New Gear |  | 2024-09-19
Touchpoints with Nursery | Confirm Seed Delivery Date |  | 2024-11-11
| Seed Into Nursery |  | 2024-10-12
| Confirm Seed Order |  | 2024-09-28
| Place Seed Order |  | 2024-08-01 | Constant

## Instructions
Calculator Instructions
To calculate your Annual Calendar:
1. On the calculations tab, edit D3 to D7 to automatically calculate below.
2. Once those calculations have populated, review to make sure the sheet is working correctly.
To export to Google Calendar:
1. Calculate your annual calendar as directed above.
2. Go to the Calendar Export Sheet
3. Do not edit any of the headings, even if they are empty they are needed for the export.
4. Copy- paste the information in the sheet, making sure to paste values only.
5. Export the Calendar Export sheet as a .csv file (delete the Calculations sheet before or after download)
6. Navigate to Google Calendar > Settings > Import & Export
7. Select the Calendar Export .csv file from your downloads and import
8. Confirm the export worked correctly by looking through your calendar and noting the events populate

## Calculations
EDIT to Calculate | When does buyer need raw kelp |  | 2025-04-30
| How many lbs to they want |  | 5000
| Growing days |  | 180
| How many lbs can you harvest/process per day |  | 1500
| Number of bad weather days a week during harvest |  | 2
Harvest | How many days will it take to harvest |  | 3.3333 |  | Calculated
| How many days will it take to harvest with bad weather buffer |  | 4.2857
| Harvest Window (Early) | Early | 2025-04-25 17:09 | 2025-04-30
| Harvest Window (Late) | Late | 2025-04-30
Touchpoints with buyers after the season | Orders for next season |  | 2025-07-30 |  | Constant
| Season Debrief |  | 2025-07-12
| Confirm Payment Received | See payment terms | 2025-07-05
| Send Invoice | ASAP | 2025-06-05
| Confirm Buyer accepts order | See inspection period | 2025-06-04
| Confirm receipt of order |  | 2025-05-30
Processing and shipping | Estimated arrival at buyer | Ask shipper | 2025-05-30
| Shipping deadline | See contract terms | 2025-05-16
| Processing Window (Start) | Start | 2025-04-25 17:09 | 2025-05-02
| Processing Window (Finish) | Finish | 2025-05-02
Touchpoints with buyers during the season | May growth update / harvest plan update | 1 week before harvest | 2025-04-18 17:09
| April growth update 2 |  | 2025-04-11 17:09
| April growth update 1 |  | 2025-03-28 17:09
| March growth update 2 |  | 2025-03-14 17:09
| March growth update 1 |  | 2025-02-28 17:09
| February growth update |  | 2025-01-07
| January growth update |  | 2024-12-08
| Post outplanting update |  | 2024-11-08
Farm Operation Deadlines | Outplanting Window (Early) | Early | 2024-10-27 17:09 | 2024-11-01
| Outplanting Window (Late) | Late | 2024-11-01
| Gear Deployment |  | 2024-10-20 17:09
| Line Preparation |  | 2024-10-13 17:09
| Receive New Gear |  | 2024-10-06 17:09
| Order New Gear |  | 2024-08-25 17:09
Touchpoints with Nursery | Confirm Seed Delivery Date |  | 2024-10-17 17:09
| Seed Into Nursery |  | 2024-09-17 17:09
| Confirm Seed Order |  | 2024-09-03 17:09
| Place Seed Order |  | 2024-08-01 |  | Constant

## Calendar Export
Subject | Start Date | Start Time | End Date | End Time | All Day Event | Description | Location
Order New Gear | 2024-08-25 17:09 |  |  |  | TRUE
Confirm Seed Order | 2024-09-03 17:09 |  |  |  | TRUE
Seed Into Nursery | 2024-09-17 17:09 |  |  |  | TRUE
Receive New Gear | 2024-10-06 17:09 |  |  |  | TRUE
Line Preparation | 2024-10-13 17:09 |  |  |  | TRUE
Confirm Seed Delivery Date | 2024-10-17 17:09 |  |  |  | TRUE
Gear Deployment | 2024-10-20 17:09 |  |  |  | TRUE
Outplanting Window (Early) | 2024-10-27 17:09 |  |  |  | TRUE | Early
Outplanting Window (Late) | 2024-11-01 |  |  |  | TRUE | Late
Post outplanting update | 2024-11-08 |  |  |  | TRUE
January growth update | 2024-12-08 |  |  |  | TRUE
February growth update | 2025-01-07 |  |  |  | TRUE
March growth update 1 | 2025-02-28 17:09 |  |  |  | TRUE
March growth update 2 | 2025-03-14 17:09 |  |  |  | TRUE
April growth update 1 | 2025-03-28 17:09 |  |  |  | TRUE
April growth update 2 | 2025-04-11 17:09 |  |  |  | TRUE
May growth update / harvest plan update | 2025-04-18 17:09 |  |  |  | TRUE | 1 week before harvest
Processing Window (Start) | 2025-04-25 17:09 |  |  |  | TRUE | Start
Processing Window (Finish) | 2025-05-02 |  |  |  | TRUE | Finish
Shipping deadline | 2025-05-16 |  |  |  | TRUE | See contract terms
Confirm receipt of order | 2025-05-30 |  |  |  | TRUE
Estimated arrival at buyer | 2025-05-30 |  |  |  | TRUE | Ask shipper
Confirm Buyer accepts order | 2025-06-04 |  |  |  | TRUE | See inspection period
Send Invoice | 2025-06-05 |  |  |  | TRUE | ASAP
Confirm Payment Received | 2025-07-05 |  |  |  | TRUE | See payment terms
Orders for next season | 2025-07-30 |  |  |  | TRUE
Season Debrief | 2025-07-12 |  |  |  | TRUE
Place Seed Order | 2024-08-01 |  |  |  | TRUE

## Calculations adjusted for timel (hidden)
EDIT on Calculations tab only | When does buyer need raw kelp |  | 2025-04-30
| How many lbs to they want |  | 5000
| Growing days |  | 180
| How many lbs can you harvest/process per day |  | 1500
| Number of bad weather days a week during harvest |  | 2
Harvest | How many days will it take to harvest |  | 3.3333 |  | 1
Harvest | How many days will it take to harvest with bad weather buffer |  | 4.2857 |  | 2
|  |  |  | DELETE | 4
|  |  |  | DELETE | 5
Touchpoints with Nursery | Place Seed Order |  | 2024-08-01 |  | 33
Touchpoints with Nursery | Confirm Seed Order |  | 2024-09-03 17:09 |  | 32
Touchpoints with Nursery | Seed Into Nursery |  | 2024-09-17 17:09 |  | 31
Touchpoints with Nursery | Confirm Seed Delivery Date |  | 2024-10-17 17:09 |  | 30
Farm Operation Deadlines | Order New Gear |  | 2024-08-25 17:09 |  | 29
Farm Operation Deadlines | Receive New Gear |  | 2024-10-06 17:09 |  | 28
Farm Operation Deadlines | Line Preparation |  | 2024-10-13 17:09 |  | 27
Farm Operation Deadlines | Gear Deployment |  | 2024-10-20 17:09 |  | 26
Farm Operation Deadlines | Outplanting Window |  | 2024-10-27 17:09 | 2024-11-01 | 24
Touchpoints with buyers during the season | Post outplanting update |  | 2024-11-08 |  | 23
Touchpoints with buyers during the season | January growth update |  | 2024-12-08 |  | 22
Touchpoints with buyers during the season | February growth update |  | 2025-01-07 |  | 21
Touchpoints with buyers during the season | March growth update 1 |  | 2025-02-28 17:09 |  | 20
Touchpoints with buyers during the season | March growth update 2 |  | 2025-03-14 17:09 |  | 19
Touchpoints with buyers during the season | April growth update 1 |  | 2025-03-28 17:09 |  | 18
Touchpoints with buyers during the season | April growth update 2 |  | 2025-04-11 17:09 |  | 17
Touchpoints with buyers during the season | May growth update / harvest plan update | 1 week before harvest | 2025-04-18 17:09 |  | 16
Harvest | Harvest Window |  | 2025-04-25 17:09 | 2025-04-30 | 3
Processing and shipping | Processing Window |  | 2025-04-25 17:09 | 2025-05-02 | 14
Processing and shipping | Shipping deadline | See contract terms | 2025-05-16 |  | 13
Touchpoints with buyers after the season | Confirm receipt of order |  | 2025-05-30 |  | 11
Processing and shipping | Estimated arrival at buyer | Ask shipper | 2025-05-30 |  | 12
Touchpoints with buyers after the season | Confirm Buyer accepts order | See inspection period | 2025-06-04 |  | 10
Touchpoints with buyers after the season | Send Invoice | ASAP | 2025-06-05 |  | 9
Touchpoints with buyers after the season | Confirm Payment Received | See payment terms | 2025-07-05 |  | 8
Touchpoints with buyers after the season | Season Debrief |  | 2025-07-12 |  | 7
Touchpoints with buyers after the season | Orders for next season |  | 2025-07-30 |  | 6
15
|  |  |  | DELETE | 25